## Tabelle1
Task | Estimated Time (hr) | Actual Time (hr)
backend: init project, user registration and auth (with api tests) | 4 | 5
backend: add currency account for user (with api tests) | 1 | 1.5
backend: submit and process transaction with job queue (with api test) | 3 | 4
backend: get state of a transaction and whole transcation history for user (with api tests) | 1 | 1
client: init project, register and login | 2 | 3
client: add currency account | 2 | 2
client: submit transaction and show history | 2 | 2
Dockerize Application | 1 | 1.5
| 16 | 20